## 내보내기 요약
이 문서는 Numbers에서 내보낸 문서입니다. 각 표가 Excel 워크시트로 변환되었습니다. 각 Numbers 시트에 있는 모든 다른 대상체는 개별 워크시트에 위치 지정되었습니다. Excel에서 공식 계산이 다를 수 있으니 유의하십시오.
Numbers 시트 이름 | Numbers 표 이름 | Excel 워크시트 이름
GoodDev_IT
| 표 1 | GoodDev_IT
작성 참고사항
| 표 1 | 작성 참고사항

## GoodDev_IT
「GoodDev」チームプロジェクトの詳細業務スケジュール表(工程図)
プロジェクト名 |  |  |  |  | チーム |  | チーム長 |  |  | チーム員
タイトル:特許を利用した小規模投資/起業者のためのクラウドファンディング |  |  |  |  | チーム 7 (GoodDeV) |  | 조 용 경（チョ・ヨンギョン） |  |  | 김남경(キム・ナンギョン) , 송재훈(ソン·ジェフン), 임창민(イム・チャンミン)
No | 담당자 | 요구사항 ID | 기능 | 개시일（예정） | 종료일(예정) | 진행율 | 진행상태 | 9월 | [29 empty] | 10
|  |  |  | 개시일（실적） | 종료일(실적) |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 조용경（チョ・ヨンギョン） | API Serve / Parsing | 특허청' Public DataBase API | 0901~ | 2019-09-03 | 100% | 完了 | bar: 9월 1 to 9월 3
|  |  |  | 0901~0903 | 2019-09-03 | bar: 9월 1 to 9월 3
2 |  | Git Structure | Git Project 作成 Branch/ Push & Pull / Teaching Git for Team | 0903~0904 | 2019-09-04 | 100% | 完了 | bar: 9월 3 to 9월 4
|  |  |  | 0903~0904 | 2019-09-04 | bar: 9월 3 to 9월 4
3 |  | AWS Server/ DB Structure | AWS Cloud Service Server open/ Cloud RDS Set / Server Work | 0904~0905 | 2019-09-05 | 100% | 完了 | bar: 9월 4 to 9월 5
|  |  |  | 0904~0905 | 2019-09-05 | bar: 9월 4 to 9월 5
4 |  | AWS DB / Domain Work | AWS DB Setting / Create Domain | 0905~0906 | 2019-09-06 | 1000% | 完了 | bar: 9월 5 to 9월 6
|  |  |  | 0905~0906 | 2019-09-06 | bar: 9월 5 to 9월 6
5 |  | MiddleSide_Member | Front + Back Function MemberSide / index | 0906~0910 | 2019-09-10 | 100% | 完了 | bar: 9월 6 to 9월 10
|  |  |  | 0906~0910 | 2019-09-10 | bar: 9월 6 to 9월 10
6 |  | MIddleSide_BoardList | Front + Back Function BoardSide / List / Paging / Write | 0910~0913 | 2019-09-13 | 100% | 完了 | bar: 9월 11 to 9월 13
|  |  |  | 0910~0913 | 2019-09-13 | bar: 9월 11 to 9월 13
7 |  | MIddleSide_BoardDetail | Front + Back Function BoardSide / Detail / delete / update | 0913~0916 | 2019-09-16 | 100% | 完了 | bar: 9월 14 to 9월 16
|  |  |  | 0913~0916 | 2019-09-16 | bar: 9월 14 to 9월 16
8 |  | MIddleSide_Servay | Front + Back Function Servay / | 0917~0919 | 2019-09-19 | 100% | 完了 | bar: 9월 16 to 9월 19
|  |  |  | 0917~0919 | 2019-09-19 | bar: 9월 16 to 9월 19
9 |  | Middleide_PatentListing_Paging | Front +Back Function Patent Paging | 0919~0921 | 2019-09-21 | 100% | 完了 | bar: 9월 19 to 9월 22
|  |  |  | 0919~0921 | 2019-09-21 | bar: 9월 19 to 9월 22
10 |  | MIddle_funding | Front + Back Function Funding List | 0923~0925 | 2019-09-25 | 100% | 完了 | bar: 9월 23 to 9월 25
|  |  |  | 0923~0925 | 2019-09-25 | bar: 9월 23 to 9월 25
11 |  | Crolling_ Set | Python -> Java ProcessBuilding Back | 0925~0927 | 2019-09-27 | 50% | 完了 | bar: 9월 25 to 9월 27
|  |  |  | 0925~0927 | 2019-09-27 | bar: 9월 25 to 9월 27
12 |  | Payment_ API | Payment API Function Back | 2019-09-26 | 2019-09-26 | 100% | 完了 | bar: 9월 26
|  |  |  | 2019-09-26 | 2019-09-26 | bar: 9월 26
13 |  | Payment_API | Payment API APPLY module (front & back) | 2019-09-26 | 2019-09-27 | 100% | 完了 | bar: 9월 26 to 9월 27
|  |  |  | 2019-09-26 | 2019-09-27 | bar: 9월 26 to 9월 27
14 |  | Chat model1 | Chat function/ Front / Back | 2019-09-28 | 2019-09-28 | 100% | 完了 | bar: 9월 28
|  |  |  | 2019-09-28 | 2019-09-28 | bar: 9월 28
15 |  | CrawdFunding / Paging | CrawdFunding front/back / Paging | 2019-09-29 | 2019-10-03 | 100% | 完了 | bar: 9월 29 to 10 3
|  |  |  | 2019-09-29 | 2019-10-03 | bar: 9월 29 to 10 3
16 |  | Stablizing | Function upgrade / setting | 2019-10-03 | 2019-10-10 | 100% | 完了 | bar: 10 3 to 10 10
|  |  |  | 2019-10-03 | 2019-10-10 | bar: 10 3 to 10 10
1 | 김남경 （キム・ナンギョン） | Front UI/UX_Index | Create Main Page | 2019-09-01 | 2019-09-02 | 100% | 完了 | bar: 9월 1 to 9월 2
|  |  |  | 2019-09-02 | 2019-09-02 | bar: 9월 1 to 9월 2
2 |  | Front UI/UX_Member(Basic Frame) | Create Member Page | 2019-09-02 | 2019-09-03 | 100% | 完了 | bar: 9월 2 to 9월 4
|  |  |  | 2019-09-02 | 2019-09-04 | bar: 9월 2 to 9월 4
3 |  | Front UI/UX_Board(Basic Frame) | Create Board List Page | 2019-09-03 | 2019-09-04 | 100% | 完了 | bar: 9월 3 to 9월 4
|  |  |  | 2019-09-03 | 2019-09-04 | bar: 9월 3 to 9월 4
4 |  | Front UI/UX_Member | Modify Member Page | 2019-09-04 | 2019-09-04 | 100% | 完了 | bar: 9월 4
|  |  |  | 2019-09-04 | 2019-09-04 | bar: 9월 4
5 |  | Front UI/UX_Member(modify), Front UI/UX_Board | Modify Member Page, Board List Page | 2019-09-05 | 2019-09-06 | 100% | 完了 | bar: 9월 5 to 9월 6
|  |  |  | 2019-09-05 | 2019-09-06 | bar: 9월 5 to 9월 6
6 |  | Front UI/UX_Mypage(Basic Frame) | Create Member -> MyPage | 2019-09-07 | 2019-09-08 | 100% | 完了 | bar: 9월 7 to 9월 8
|  |  |  | 2019-09-07 | 2019-09-08 | bar: 9월 7 to 9월 8
7 |  | Front UI/UX_Survey all part | Create Survey Page | 2019-09-09 | 2019-09-10 | 100% | 完了 | bar: 9월 9 to 9월 10
|  |  |  | 2019-09-09 | 2019-09-10 | bar: 9월 9 to 9월 10
8 |  | Front UI/UX_Funding(list, Basic Frame) | Create CrowdFunding Page | 2019-09-11 | 2019-09-12 | 100% | 完了 | bar: 9월 11 to 9월 12
|  |  |  | 2019-09-11 | 2019-09-12 | bar: 9월 11 to 9월 12
9 |  | Front UI/UX_patent search form, search menu | Search Patent, Search Menu Page | 2019-09-12 | 2019-09-13 | 100% | 完了 | bar: 9월 12 to 9월 13
|  |  |  | 2019-09-12 | 2019-09-13 | bar: 9월 12 to 9월 13
10 |  | Front UI/UX_css all modify | Modify bootstrap、jQuery、css etc. | 2019-09-14 | 2019-09-15 | 100% | 完了 | bar: 9월 14 to 9월 15
|  |  |  | 2019-09-15 | 2019-09-15 | bar: 9월 15
11 |  | Front UI/UX_item write form, Detail | Create Item Page(Write form, Detail) | 2019-09-16 | 2019-09-16 | 100% | 完了 | bar: 9월 16
|  |  |  | 2019-09-16 | 2019-09-16 | bar: 9월 16
12 |  | Front UI/UX_survey result | Create Survey Result Page | 2019-09-17 | 2019-09-18 | 100% | 完了 | bar: 9월 17 to 9월 18
|  |  |  | 2019-09-17 | 2019-09-18 | bar: 9월 17 to 9월 18
13 |  | Front UI/UX_patent search form, search menu | Create Search form, Modify Search Menu Page | 2019-09-18 | 2019-09-19 | 100% | 完了 | bar: 9월 18 to 9월 19
|  |  |  | 2019-09-18 | 2019-09-19 | bar: 9월 18 to 9월 19
14 |  | Front UI/UX_funding Write form, Detail | Create Funding Write Page, Detail Page | 2019-09-20 | 2019-09-22 | 100% | 完了 | bar: 9월 20 to 9월 22
|  |  |  | 2019-09-20 | 2019-09-22 | bar: 9월 20 to 9월 22
15 |  | Front UI/UX_Chat | Create RealTime Chat UI(Index(anonymous), Funding(1:1)) | 2019-09-23 | 2019-09-24 | 100% | 完了 | bar: 9월 23 to 9월 24
|  |  |  | 2019-09-23 | 2019-09-24 | bar: 9월 23 to 9월 24
16 |  | Front UI/UX_css all modify | Modify bootstrap, jQuery, css, Stabilizing | 2019-09-25 | 2019-10-10 | 100% | 完了 | bar: 9월 25 to 10 10
|  |  |  | 2019-09-25 | 2019-10-10 | bar: 9월 25 to 10 10
17
18
1 | 송재훈 (ソン・ ジェフン) | DB_design_01 | Designed DB, ER-D and Usecase | 2019.09.01 | 2019.09.05 | 100% | 完了 | bar: 9월 1 to 9월 5
|  |  |  | 2019.09.01 | 2019.09.05 | bar: 9월 1 to 9월 5
2 |  | DB_design_02 | Designed DB / Designed VO | 2019.09.06 | 2019.09.06 | 100% | 完了 | bar: 9월 6
|  |  |  | 2019.09.06 | 2019.09.06 | bar: 9월 6; 9월 14
3 |  | DB_mapping_01 | Designed MemeberMapper(Query,Dao) | 2019.09.09 | 2019.09.09 | 100% | 完了 | bar: 9월 9; 9월 14
|  |  |  | 2019.09.09 | 2019.09.09 | bar: 9월 9; 9월 14
4 |  | DB_mapping_02 | Designed ItemMapper and MTIMapper(Query,Dao) | 2019.09.10 | 2019.09.10 | 100% | 完了 | bar: 9월 10; 9월 14
|  |  |  | 2019.09.10 | 2019.09.10 | bar: 9월 10; 9월 14
5 |  | DB_mapping_03 | Designed boardMapper and replyMapper(Query,Dao) | 2019.09.11 | 2019.09.11 | 100% | 完了 | bar: 9월 11; 9월 14
|  |  |  | 2019.09.11 | 2019.09.11 | bar: 9월 11; 9월 14
6 |  | DB_mapping_04 | Designed historyMapper(Query,Dao) | 2019.09.12 | 2019.09.12 | 100% | 完了 | bar: 9월 12; 9월 14
|  |  |  | 2019.09.12 | 2019.09.12 | bar: 9월 12; 9월 14
7 |  | DB_mapping_05 | Designed item_SurveyMapper(Query, Dao) | 2019.09.13 | 2019.09.13 | 100% | 完了 | bar: 9월 13 to 9월 14
|  |  |  | 2019.09.13 | 2019.09.13 | bar: 9월 13 to 9월 14
8 |  | DB_mapping_06 | Designed fundingMapper(Query,Dao) | 2019.09.14 | 2019.09.14 | 100% | 完了 | bar: 9월 14
|  |  |  | 2019.09.14 | 2019.09.14 | bar: 9월 14
9 |  | DB_mapping_07 | Designed patentsubMapper, patentMapper(Query,Dao) | 2019.09.16 | 2019.09.17 | 100% | 完了 | bar: 9월 14; 9월 16 to 9월 17
|  |  |  | 2019.09.19 | 2019.09.19 | bar: 9월 14; 9월 19
10 |  | DB_designChange_01 | Altered DB(Added table : fundingOption) | 2019.09.16 | 2019.09.16 | 100% | 完了 | bar: 9월 16
|  |  |  | 2019.09.16 | 2019.09.16 | bar: 9월 16
11 |  | DB_mapping_08 | Designed fundingOptionMapper(Query,Dao) | 2019.09.17 | 2019.09.17 | 100% | 完了 | bar: 9월 17
|  |  |  | 2019.09.17 | 2019.09.17 | bar: 9월 17
12 |  | DB_designChange_02 | Altered DB(Added table : Document, Altered table : Patent) | 2019.09.18 | 2019.09.18 | 100% | 完了 | bar: 9월 18
|  |  |  | 2019.09.18 | 2019.09.18 | bar: 9월 18
13 |  | DB_designChange_03 | Altered DB(Update table : Survey)and Revised item_SurveyMapper | 2019.09.18 | 2019.09.18 | 100% | 完了 | bar: 9월 19
|  |  |  | 2019.09.18 | 2019.09.18 | bar: 9월 19
14 |  | DB_designChange_04 | Altered DB(Update table : Survey) | 2019.09.18 | 2019.09.18 | 100% | 完了 | bar: 9월 20
|  |  |  | 2019.09.18 | 2019.09.18 | bar: 9월 20
15 |  | MIddleSide_survey_list | Designed Front +Back Function(survey_list.jsp) | 2019.09.24 | 2019.09.24 | 100% | 完了 | bar: 9월 23
|  |  |  | 2019.09.24 | 2019.09.24 | bar: 9월 23
16 |  | MIddleSide_survey_Detail | Designed Front +Back Function(survey_Detail.jsp) | 2019.09.25 | 2019.09.25 | 100% | 完了 | bar: 9월 24 to 9월 25
|  |  |  | 2019.09.25 | 2019.09.25 | bar: 9월 24 to 9월 25
17 |  | MIddleSide_survey_form | Designed Front +Back Function(survey_form.jsp) | 2019.09.26 | 2019.09.26 | 100% | 完了 | bar: 9월 26
|  |  |  | 2019.09.26 | 2019.09.26 | bar: 9월 26
17 |  | MIddleSide_survey_result | Designed Front +Back Function(survey_result.jsp) | 2019.09.27 | 2019.09.27 | 100% | 完了 | bar: 9월 27
|  |  |  | 2019.09.27 | 2019.09.27 | bar: 9월 27
18 |  | MIddleSide_chat_popup | Designed Front +Back Function(chat_popup.jsp) | 2019.09.30 | 2019.10.02 | 100% | 完了 | bar: 9월 30 to 10 2
|  |  |  | 2019.09.30 | 2019.10.02 | bar: 9월 30 to 10 2
18 |  | MIddleSide_downLoad | Designed downLoad Function(Board_Detail.jsp, item_Detail.jsp, patent_use_list.jsp, search_menu.jsp, survey_Detail.jsp) | 2019.10.03 | 2019.10.06 | 100% | 完了 | bar: 10 3 to 10 6
|  |  |  | 2019.10.03 | 2019.10.06 | bar: 10 3 to 10 6
19 |  | Project debugging | Debugged and checked function (Survey section, chat_popup.jsp) | 2019.10.07 | 2019.10.10 | 100% | 完了 | bar: 10 7 to 10 10
|  |  |  | 2019.10.07 | 2019.10.10 | bar: 10 7 to 10 10
20
1 | 임창민 | public Data API | Parshing | 2019-09-03 | 2019-09-04 | 100% | 完了 | bar: 9월 3 to 9월 4
|  |  |  | 2019-09-03 | 2019-09-04 | bar: 9월 3 to 9월 4
2 |  | public Data DB save | public Data DB Insert | 2019-09-03 | 2019-09-04 | 100% | 完了 | bar: 9월 3 to 9월 5
|  |  |  | 2019-09-03 | 2019-09-05 | bar: 9월 3 to 9월 5
3 |  | AWS Server | AWS Server build | 2019-09-04 | 2019-09-05 | 100% | 完了 | bar: 9월 4 to 9월 5
|  |  |  | 2019-09-04 | 2019-09-05 | bar: 9월 4 to 9월 5
4 |  | Python Crawling studying | jupyter note로 selenium , BeautifulSoup Parshing | 2019-09-06 | 2019-09-08 | 100% | 完了 | bar: 9월 6 to 9월 8
|  |  |  | 2019-09-06 | 2019-09-08 | bar: 9월 6 to 9월 8
5 |  | middleSide_member | member_insert, member_update, member_login, member_delete | 2019-09-09 | 2019-09-10 | 100% | 完了 | bar: 9월 9 to 9월 10
|  |  |  | 2019-09-09 | 2019-09-10 | bar: 9월 9 to 9월 10
6 |  | MIddleSide_myPage | PatentList, ItemList, CloudFundingList, subvey, Q&A List | 2019-09-11 | 2019-09-22 | 100% | 完了 | bar: 9월 11 to 9월 22
|  |  |  | 2019-09-11 | 2019-09-23 | bar: 9월 11 to 9월 23
7 |  | middleSide_ item, history | item_search, histroy_insert, history_list | 2019-09-21 | 2019-09-24 | 100% | 完了 | bar: 9월 21 to 9월 24
|  |  |  | 2019-09-22 | 2019-09-24 | bar: 9월 22 to 9월 24
8 |  | MIddleSide_Patent, Patent, document | Pti _insert, Document_insert, Patent_search,patent_useList | 2019-09-25 | 2019-09-29 | 100% | 完了 | bar: 9월 25 to 9월 29
|  |  |  | 2019-09-25 | 2019-09-29 | bar: 9월 25 to 9월 29
9 |  | Python Crawling | Gmarket Crawling → item_search link | 2019-09-29 | 2019-10-04 | 100% | 完了 | bar: 9월 29 to 10 4
|  |  |  | 2019-09-30 | 2019-10-04 | bar: 9월 30 to 10 4
10 |  | middle_Side chat, payment | middle_Side chat, payment | 2019-10-04 | 2019-10-06 | 100% | 完了 | bar: 10 4 to 10 7
|  |  |  | 2019-10-04 | 2019-10-07 | bar: 10 4 to 10 7
11 |  | middle_Side servey, board, fund Link | middle_Side servey, board, fund Link | 2019-10-08 | 2019-10-09 | 100% | 完了 | bar: 10 8 to 10 9
|  |  |  | 2019-10-08 | 2019-10-09 | bar: 10 8 to 10 9
12 |  | Project debugging | Project debugging | 2019-10-08 | 2019-10-10 | 100% | 完了 | bar: 10 8 to 10 10
|  |  |  | 2019-10-08 | 2019-10-10 | bar: 10 8 to 10 10

## 작성 참고사항
□ | 予定 | ■ | 実作業 | 備考 | 業務遅延発生時、メモ欄に遅延理由を作成すること!